## Product Backlog
[Group 3 Shreya K. & Tirth S.]
[Mid-term Phase 0]
Product Backlog | [5 empty] | Use index colors to show revisions on task time
Unique ID | Task | Sprint | Estimated time (minutes) | Time after Iteration 1 | Time after Iteration 2 | Index | Information
Target Time
1 | Plan and Design |  | 390 | 0 | 0 |  | Revised Target Time
1.1 | Literature Survey and Defining the deliverables | 1 | 90 |  |  |  | Actual Time Taken
1.2 | Discuss Software Architcture | 1 | 30 |  |  |  | New Task Added
1.3 | Researching Open Source Libraries | 1 | 60
1.4 | Making Github Repository | 1 | 30
1.5 | Planning Tasks and Assigning responsibilites | 1 | 30
1.6 | Initial Coding and Enivronment Setup | 1 | 120
1.7 | Documentation for Phase 0 | 1 | 30
1.8 | Future Implementation Planing | 1 | 30
1.9 | Updating ReadMe | 1 | 30
2 | Implementation |  | 0 | 0 | 0
2.1 |  | 2
Remaining effort
Total effort time

## Iteration backlog - 1
[Group Number and members]
[Project title]
Iteration Backlog 1
Unique ID | Task | Target time (minutes) | Actual Time | Status
1 | Plan and Design | 0 | 0

## Iteration backlog - 2
[Group Number and members]
[Project title]
Iteration Backlog 2
Unique ID | Task | Target time (minutes) | Actual Time | Status
2 | Implementation | 0 | 0

## Work log
[Group Number and members]
[Project title]
Work/ Time log
Process Enactment |  | Pair Programming Roles | [5 empty] | Interrupt
Task / Step | Comment | Driver | Navigator | Design Keeper | Date | Start | End | # | Time | Clean time
Iteration 1
[11 empty] | Task / Step | Meaning
[11 empty] | Pri | backlog prioritization
[11 empty] | Div | dividing the change into smaller parts
[11 empty] | Ini | software change initiation
[11 empty] | CL | concept location
[11 empty] | IA | impact analysis
[11 empty] | Ref | refactoring and testing
[11 empty] | Act | actualization and testing
[11 empty] | Test | other testing
[11 empty] | Bas | baseline build
[11 empty] | Rel | release
Iteration 2 | [10 empty] | Ex | exceptional task or phase